## Sheet1
1	Display of restricted Forum on Forum List page	The Restricted Forum needs to be displayed to the allowed segment only. So for example if the allowed user is Women 30+ then this forum should be only visible to women who are 30+ and not to any other segment.	Done
2	Thumbnail Image of the User who added a Topic needs to be diplayed	The thumbnail image of the user who adds a topic needs to displayed in the left hand side (as currently done for the users who comment)	Till now we didnt did any image part from where we want to fetch image or user will upload it we don't know. And if we add the image of user then the design of the page will be changed.
3	Ability to Edit the Forum name and description	The admin should have the option to Edit the Forum name and description post creating a Forum. This could be small "Pen" Icon available on top of the Forum. On the click of it - the admin could edit the Forum Name and description.	Done
4	Forum - Admin Adding new Forum (Segment Restriction)	The Segment Restrictions need to work as follows: / Options available on screen: / - Allow all registered users (checked by default) / OR / - Allow / Gender (dropdown - All (default selection), Male, Female ) / Age dropdown - All , Below 30, 30+, 35+, 40+ / Location - all states, allow multiple selection )	This one is jiby section the changes are pretty simple but i don't want to touch his code thats why i didn't touched this part.
5	User Adding a Topic to a Forum	The action button needs to be called "Add New Topic" / - When user clicks on it- a pop up screen should allow enter new topic. / - On "Submit" - a message should state that - The topic will be posted soon after review. And henceforth close the pop up screen / - The comments link should also display the number of comments in brackets. The link should be displayed as clickable (Blue color) for the user to know it clickable / - Add new topic and comments would be disabled for users who have not joined the forum . They should be able to view the list of topics and would have an action button - "Join This Forum" / - User should have the ability to "rate a topic" - out of 5 stars	Done